## Sheet2
PROJECT BACKLOG
EvoSoft
<SBS>
[9 empty] | PLANING |  |  |  |  | EXECUTING
User Story |  |  |  | EFFORT |  |  | Pair |  | DISCIPLINES |  |  |  |  | DISCIPLINES
ID | NAME | PRIORITY | SPRINT | PLANNED | EXECUTED | STATUS | Responsability | SPRINT ID | REQUIREMENTS | DESIGN | CODING | TESTING | INTEGRATION | REQUIREMENTS | DESIGN | CODING | TESTING | INTEGRATION
SNX-UC1 | Autenticar usuario | 10% |  | 15 | 3 | Not Stated | Jean Carlos | SPRINT-1 |  | 10 | 15 | 20 | 16 |  | 9 | 8 | 0 | 0
SNX-UC2 | Registrar conductor | 15% |  | 13 | 3 | In Progress | Diego | SPRINT-1 |  | 9 | 14 | 18 | 14 |  | 8 | 8 | 0 | 0
SNX-UC3 | Actualizar datos del conductor | 11% |  | 13 | 1 | Stand by | Jean Carlos | SPRINT-1
SNX-UC4 | Suspender usuario | 7% |  | 14 | 3 | In Progress | Aldo | SPRINT-1 |  | 14 | 18 | 22 | 16 |  | 6 | 5 | 0 | 0
SNX-UC5 | Visualizar listado de conductores | 10% |  | 13 | 3 | In Progress | Richard | SPRINT-1 |  | 11 | 17 | 21 | 16 |  | 11 | 14 | 0 | 0
SNX-UC6 | Registrar vehiculo | 15% |  | 13 |  | Not Stated | Diego | SPRINT-2
SNX-UC7 | Actualizar datos del vehiculo | 11% |  | 13 |  | Not Stated | Jean Carlos | SPRINT-2
SNX-UC8 | Suspender vehiculo | 11% |  | 13 |  | Not Stated | Aldo | SPRINT-2
SNX-UC9 | Visualizar listado de vehiculos | 10% |  | 13 |  | Not Stated | Richard | SPRINT-2